## Kick-Off Checklist (Phase 0)
Confidentiality Notice: This document is private and confidential. If received in error, please destroy and notify TT Electronics (TT). TT does not intend to waive confidentiality or privilege. Dissemination, use of or reliance upon this document is prohibited when received in error. © TT Electronics PLC
Kick-Off Review Checklist (Pre-Kick-Off)
[12 empty] | SE - System Engineer | SE | Y | PASS
| Title of Project | [10 empty] | LE - Lead Engineer | LE | N | FAIL
| Project Manager | [10 empty] | PE - Power Electronics | PE
| Lead Engineer | [10 empty] | DE - Digitial Electronics | DE
| Description of Project | [10 empty] | ME - Mechanical Engineer | ME
| Customer | [10 empty] | PM - Program Manager | PM
| Key deliverable schedule | [10 empty] | ECAD - ECAD Engineer | ECAD
| Security Classififcation | [10 empty] | ESE - Embedded Software Engineer | ESE
Date of Gate Review
| Category | Item | Description | PASS/FAIL | Evidence (Screen Shots/ Jama Links/ File Location) | Notes / Actions | Action Status | Action Due Date | Who | Reviewer (Titles) | Reviewed (Y/N)
| Documents | SEMP | Has the System Engineering Management Plan been created & approved?
| Documents | PMP | Has the Program Management Plan been created & approved?
| Files | Organizational Structure | Are the files paths created?
| Managament | Resources Allocation | Has all the resources been assigned?
| Programatic | Milestones | Are all the major program milestones been confirmed & agreed apon?
| Programatic | Deliverables | Has all the major program deliverables been confirmed & agreed apon?
| Programatic | Communication | Has the internal Program Stand-ups been assigned dates & times?
| Technical | Communication | Has the internal Technical Stand-ups been assigned dates & times?
| Programatic | Configuration Management | Has the configuration management plan been impletmented?
| Managament | Training | Have all the nessasary training been complete (e.g. QEW / Non-QEW / OPSEC - CUI)
| Programatic | Part Numbers | Has part numbers been created for top level & Subsystems?
Documentation Naming
Notes: (record any key points discussed but not covered elsewhere)
| Gate Outcome: |  |  | Date of next review
Approval:
| Technical Lead |  |  | Date:
| System Engineer |  |  | Date:
| Embedded Electronics (Digital) Engineer |  |  | Date:
| Power Electronics Engineer |  |  | Date:
| Mechanical Engineer |  |  | Date:
| Program Manager |  |  | Date:
| Design Engineering Manager |  |  | Date:
| Director of Engineering |  |  | Date:

## System Level Review (Phase 1)
Confidentiality Notice: This document is private and confidential. If received in error, please destroy and notify TT Electronics (TT). TT does not intend to waive confidentiality or privilege. Dissemination, use of or reliance upon this document is prohibited when received in error. © TT Electronics PLC
System Level Review Checklist (SRR)
[13 empty] | SE - System Engineer | SE | SRR | Y | PASS
| Title of Project | [11 empty] | LE - Lead Engineer | LE | PDR | N | FAIL
| Project Manager | [11 empty] | PE - Power Electronics | PE | CDR
| Lead Engineer | [11 empty] | DE - Digitial Electronics | DE | TRR
| Description of Project | [11 empty] | ME - Mechanical Engineer | ME
| Customer | [11 empty] | PM - Program Manager | PM
| Key deliverable schedule | [11 empty] | ECAD - ECAD Engineer | ECAD
| Security Classififcation | [11 empty] | ESE - Embedded Software Engineer | ESE
Date of Gate Review
| Category | Item | Description | PASS/FAIL | Evidence (Screen Shots/ Jama Links/ File Location/Hyper-Link) | Notes / Actions | Action Status | Action Due Date | Who | Reviewer (Titles) | Reviewed (Y/N) | Phase Gate Needed
| Requirements | Requirements Completeness | Are all functional and non-functional requirements clearly defined and documented? | [8 empty] | SRR
| Requirements | Traceability | Can every requirement be traced to a system function or subsystem? | [8 empty] | PDR
| Requirements | Measurability | Are all requirements measurable and testable? | [8 empty] | CDR
| Requirements | Constraints | Are constraints (cost, size, power, environment) clearly defined? | [8 empty] | PDR
| Requirements | Regulatory | Are all applicable regulatory and compliance requirements identified?
| Requirements | Operating Conditions | Are all operating conditions (temperature, voltage, humidity, vibration) defined?
| Requirements | Use Cases | Are all intended use cases and edge cases defined?
| Requirements | Failure Modes | Are expected failure modes and safe states defined?
| Architecture | Block Diagram | Is a complete and accurate system block diagram available?
| Architecture | Functional Partitioning | Are system functions logically partitioned into subsystems?
| Architecture | Complexity | Is the architecture as simple as possible while meeting requirements?
| Architecture | Scalability | Can the architecture scale for future features or variants?
| Architecture | Modularity | Are subsystems modular and loosely coupled?
| Architecture | Technology Choices | Are chosen technologies appropriate and justified?
| Architecture | Risk Areas | Are high-risk areas identified early in the architecture?
| Architecture | Single Points of Failure | Are single points of failure identified and mitigated?
| Power | Power Sources | Are all power sources (battery, AC, external supply) clearly defined?
| Power | Power Budget | Is a complete system power budget calculated for all modes?
| Power | Efficiency Targets | Are efficiency targets defined for the system?
| Power | Power Tree | Is a high-level power tree defined (rails, conversions, sequencing)?
| Power | Peak Loads | Are peak and transient loads identified?
| Power | Startup Behavior | Is system startup behavior defined and safe?
| Power | Shutdown Behavior | Is safe shutdown behavior defined?
| Power | Redundancy | Is power redundancy required and implemented?
| Power | Thermal Impact | Has power dissipation impact on system thermals been estimated?
| Compute | Processor Selection | Is the selected processor/FPGA appropriate for performance needs?
| Compute | Resource Margin | Are CPU, memory, and peripheral margins sufficient?
| Compute | Memory Architecture | Is memory type (DDR, Flash, etc.) appropriate and sufficient?
| Compute | Boot Strategy | Is a robust boot strategy defined (boot source, fallback)?
| Compute | Firmware Update | Is firmware update strategy defined (OTA, recovery, fail-safe)?
| Compute | Latency | Are latency requirements identified and achievable?
| Compute | Real-Time Needs | Are real-time constraints identified and supported?
| Interfaces | External Interfaces | Are all external interfaces (USB, Ethernet, CAN, etc.) defined?
| Interfaces | Internal Interfaces | Are internal communication buses clearly defined?
| Interfaces | Bandwidth | Are bandwidth requirements defined and achievable?
| Interfaces | Protocol Selection | Are communication protocols appropriate and justified?
| Interfaces | Signal Levels | Are voltage levels compatible across interfaces?
| Interfaces | Isolation Needs | Is electrical isolation required for any interfaces?
| Interfaces | Connector Strategy | Are connector types and counts defined?
| EMI | Compliance Targets | Are EMI/EMC compliance standards identified?
| EMI | Noise Sources | Are major noise sources identified (switching, clocks, RF)?
| EMI | Shielding Strategy | Is a system-level shielding strategy defined?
| EMI | Filtering Strategy | Are filtering approaches defined at system boundaries?
| EMI | Grounding Strategy | Is grounding philosophy (chassis, digital, analog) defined?
| Thermal | Heat Sources | Are major heat sources identified?
| Thermal | Cooling Strategy | Is cooling strategy defined (passive, active, conduction)?
| Thermal | Temperature Limits | Are component/system temperature limits defined?
| Thermal | Environment | Are environmental thermal conditions considered?
| Thermal | Derating | Is thermal derating strategy defined?
| Mechanical | Envelope | Are size and form-factor constraints defined?
| Mechanical | Mounting | Are mounting methods and constraints defined?
| Mechanical | Connectors | Are connector locations aligned with enclosure design?
| Mechanical | Serviceability | Is access for service/debug considered?
| Mechanical | Environmental Sealing | Are sealing/IP requirements defined?
| Safety | Standards Compliance | Are applicable safety standards identified (UL, IEC, etc.)?
| Safety | Hazard Analysis | Has a hazard/risk analysis been performed?
| Safety | Fault Handling | Are fault detection and safe states defined?
| Reliability | MTBF Targets | Are reliability targets defined?
| Reliability | Redundancy | Is redundancy required for critical systems?
| Reliability | Environmental Stress | Are environmental stresses accounted for?
| Verification | Test Strategy | Is a system-level test strategy defined?
| Verification | Validation Plan | Are validation methods defined for each requirement?
| Verification | Instrumentation | Are measurement methods/tools identified?
| Verification | Prototyping | Is a prototyping plan defined?
| Verification | Success Criteria | Are clear pass/fail criteria defined?
| Programatic | Volume | Are production volume targets defined?
| Programatic | Cost Targets | Are cost targets realistic and defined?
| Programatic | Supply Chain | Are critical components available and low risk?
| Manufacturing | Test Strategy | Is manufacturing test strategy defined?
| Manufacturing | Assembly | Are assembly constraints considered?
| Documentation | Clarity | Are architecture documents clear and complete?
| Documentation | Requirements Document | Has the System Requirment Document been created & Approved
| Documentation | Review Readiness | Is the design ready for schematic capture?
| Gotchas | Undefined Power Tree | Is the power tree fully defined before schematic work begins?
| Gotchas | Missing Requirements | Are there any undefined or ambiguous requirements?
| Gotchas | Overcomplex Design | Is the design more complex than necessary?
| Gotchas | No Margin | Are margins insufficient or undefined?
| Gotchas | Late EMI Consideration | Has EMI been considered early, not deferred to layout?
| Gotchas | Thermal Oversight | Has thermal impact been underestimated?
| Category | Item | Description | PASS/FAIL | Evidence (Screen Shots/ Jama Links/ File Location) | Notes / Actions | Action Status | Action Due Date | Who | Reviewer (Titles) | Reviewed (Y/N)
| Documentation | Clarity | Are architecture documents clear and complete?
| Documentation | Interfaces | Are interface control documents (ICDs) defined?
| Documentation | Assumptions Matrix | Are all design assumptions documented?
| Documentation | Risks Matrix | Are risks clearly documented and tracked?
| Documentation | Requirements Document | Has the System Requirment Document been created & Approved
Documentation
Notes: (record any key points discussed but not covered elsewhere)
| Gate Outcome: |  |  | Date of next review
Approval:
| Technical Lead |  |  | Date:
| System Engineer |  |  | Date:
| Embedded Electronics (Digital) Engineer |  |  | Date:
| Power Electronics Engineer |  |  | Date:
| Mechanical Engineer |  |  | Date:
| Program Manager |  |  | Date:
| Design Engineering Manager |  |  | Date:
| Director of Engineering |  |  | Date:

## Schematic Review (Phase 2)
Confidentiality Notice: This document is private and confidential. If received in error, please destroy and notify TT Electronics (TT). TT does not intend to waive confidentiality or privilege. Dissemination, use of or reliance upon this document is prohibited when received in error. © TT Electronics PLC
Schematic Review Checklist (Power Electronics/ Embedded Systems) - PDR/CDR
[13 empty] | SE - System Engineer | SE | SRR | Y | PASS
| Title of Project | [11 empty] | LE - Lead Engineer | LE | PDR | N | FAIL
| Project Manager | [11 empty] | PE - Power Electronics | PE | CDR
| Lead Engineer | [11 empty] | DE - Digitial Electronics | DE | TRR
| Description of Project | [11 empty] | ME - Mechanical Engineer | ME
| Customer | [11 empty] | PM - Program Manager | PM
| Key deliverable schedule | [11 empty] | ECAD - ECAD Engineer | ECAD
| Security Classififcation | [11 empty] | ESE - Embedded Software Engineer | ESE
Date of Gate Review
| Category | Item | Description | PASS/FAIL | Evidence (Screen Shots/ Jama Links/ File Location) | Notes / Actions | Action Status | Action Due Date | Who | Reviewer (Titles) | Reviewed (Y/N) | Phase Gate Needed
| Architecture | Requirements Traceability | Does the schematic fully implement all system requirements and specifications? | [8 empty] | CDR
| Architecture | Block Diagram Alignment | Does the schematic match the approved system/block diagram? | [8 empty] | PDR
| Architecture | Power Tree | Is the complete power tree defined, including all rails and dependencies? | [8 empty] | CDR
| Architecture | Interface Definition | Are all external and internal interfaces clearly defined and documented? | [8 empty] | PDR
| Architecture | Design Margins | Are voltage, current, and timing margins clearly defined?
| Architecture | Startup/Shutdown | Are power-up and power-down sequences defined and safe?
| Power | Topology Selection | Is the chosen power topology appropriate (buck, boost, flyback, LDO, etc.)?
| Power | Controller Selection | Is the regulator/controller suitable for load, efficiency, and switching frequency?
| Power | Input Range | Does the design handle full input voltage range including transients?
| Power | Output Accuracy | Are output voltage tolerances within system requirements?
| Power | Current Capability | Can the regulator supply peak and continuous current with margin?
| Power | Switching Frequency | Is switching frequency appropriate for efficiency and EMI trade-offs?
| Power | Inductor Selection | Is the inductor properly sized for ripple current and saturation limits?
| Power | Capacitor Selection | Are input/output capacitors sized for ripple, ESR, and stability?
| Power | Compensation Network | Is loop compensation designed and verified for stability?
| Power | Feedback Network | Are feedback resistors correctly calculated for output voltage?
| Power | Soft Start | Is soft-start implemented to limit inrush current?
| Power | Protection Features | Are OVP, UVLO, OCP, SCP, OTP implemented where required?
| Power | Efficiency | Has efficiency been estimated across load range?
| Power | Power Dissipation | Are worst-case losses calculated for all components?
| PDN | Rail Definition | Are all voltage rails clearly defined and labeled?
| PDN | Decoupling Strategy | Is a complete decoupling strategy defined (bulk + mid + high frequency)?
| PDN | Capacitor Values | Are capacitor values selected based on frequency response needs?
| PDN | Placement Intent | Is intended placement (close to pins) clearly implied/documented?
| PDN | Load Transients | Can the PDN handle transient load steps?
| PDN | Sequencing | Are rail sequencing requirements defined and enforced?
| PDN | Ferrite Beads | Are ferrite beads used appropriately and not overused?
| Processor | Part Selection | Is the processor/MCU/FPGA appropriate for performance and peripherals?
| Processor | Power Rails | Are all required voltage rails present and correctly assigned?
| Processor | Decoupling | Are decoupling capacitors specified per manufacturer guidelines?
| Processor | Boot Configuration | Are boot mode pins correctly configured?
| Processor | Reset Circuit | Is reset circuitry properly designed (timing, pull-ups, supervisor)?
| Processor | Clock Source | Is the clock source correctly selected and stable?
| Processor | Oscillator Network | Are crystal load capacitors correctly calculated?
| Processor | Programming Interface | Is JTAG/SWD/UART programming interface included and accessible?
| Processor | Unused Pins | Are unused pins handled per datasheet recommendations?
| Processor | IO Voltage Levels | Are IO voltage levels compatible with connected devices?
| Signal Integrity | High-Speed Interfaces | Are high-speed interfaces (DDR, USB, PCIe, etc.) properly defined?
| Signal Integrity | Differential Signals | Are differential pairs clearly identified and grouped?
| Signal Integrity | Termination Strategy | Are termination schemes defined for critical signals?
| Signal Integrity | Length Matching Needs | Are nets requiring length matching clearly identified?
| Signal Integrity | Impedance Requirements | Are impedance requirements documented for layout?
| Signal Integrity | Signal Levels | Are signal voltage levels and thresholds compatible across interfaces?
| EMI | Input Filtering | Are input filters (LC, π filters) included where required?
| EMI | Output Filtering | Are output filters adequate to reduce noise emissions?
| EMI | Shielding Strategy | Is a shielding/grounding strategy defined?
| EMI | Switching Nodes | Are noisy switching nodes minimized and identified?
| EMI | IO Protection | Are external interfaces protected against noise and ESD?
| Components | Voltage Rating | Are all components rated above maximum operating voltage?
| Components | Current Rating | Are components rated for worst-case current conditions?
| Components | Temperature Rating | Are components suitable for operating temperature range?
| Components | Derating | Is proper derating applied (voltage, current, power)?
| Components | Availability | Are components available and not obsolete or long lead-time?
| Components | Package Selection | Are packages suitable for thermal and assembly constraints?
| Protection | ESD Protection | Is ESD protection included on all external interfaces?
| Protection | Reverse Polarity | Is reverse polarity protection implemented if needed?
| Protection | Overvoltage | Are overvoltage protection mechanisms included?
| Protection | Inrush Control | Is inrush current properly limited?
| Protection | Fault Handling | Are fault conditions handled safely?
| Reliability | Redundancy | Is redundancy included where required?
| Reliability | Safety Compliance | Does the design meet applicable safety standards?
| Interfaces | Connector Selection | Are connectors appropriate for current, voltage, and environment?
| Interfaces | Pinout | Are connector pinouts logical and error-resistant?
| Interfaces | Protection | Are interface lines protected (ESD, filtering)?
| Interfaces | Signal Integrity | Are high-speed connectors matched to signal requirements?
| Interfaces | Labeling | Are all connectors and signals clearly labeled?
| Simulation | Power Simulation | Has power stage been simulated (efficiency, ripple, stability)?
| Simulation | Stability Analysis | Has loop stability (Bode plot) been verified?
| Simulation | Thermal Estimate | Has thermal performance been estimated?
| Simulation | Worst Case | Has worst-case/tolerance analysis been performed?
| Simulation | Transient Response | Has transient response been evaluated?
| Documentation | Clarity | Is the schematic clean, readable, and logically organized?
| Documentation | Net Naming | Are nets clearly and consistently named?
| Documentation | Notes | Are critical design notes and assumptions documented?
| Documentation | Revision Control | Is revision history properly maintained?
| Documentation | Design Intent | Is design intent clearly communicated to layout engineers?
| Any Gotchas | Missing Pull-ups | Are all required pull-ups/pull-downs included?
| Any Gotchas | Incorrect Feedback | Is regulator feedback network free from calculation errors?
| Any Gotchas | Unstable Compensation | Has compensation been validated (not copied blindly)?
| Any Gotchas | Crystal Errors | Are crystal circuits correctly designed per datasheet?
| Any Gotchas | Floating Nets | Are there any unintended floating nets or pins?
| Any Gotchas | Miswired Power Pins | Are all IC power pins correctly connected?
Notes: (record any key points discussed but not covered elsewhere)
| Gate Outcome: |  |  | Date of next review
Approval:
| Technical Lead |  |  | Date:
| System Engineer |  |  | Date:
| Embedded Electronics (Digital) Engineer |  |  | Date:
| Power Electronics Engineer |  |  | Date:
| Mechanical Engineer |  |  | Date:
| Program Manager |  |  | Date:
| Design Engineering Manager |  |  | Date:
| Director of Engineering |  |  | Date:

## PCB Layout Review (Phase 3)
Confidentiality Notice: This document is private and confidential. If received in error, please destroy and notify TT Electronics (TT). TT does not intend to waive confidentiality or privilege. Dissemination, use of or reliance upon this document is prohibited when received in error. © TT Electronics PLC
PCB Layout Review Checklist (CDR)
[13 empty] | SE - System Engineer | SE | SRR | Y | PASS
| Title of Project | [11 empty] | LE - Lead Engineer | LE | PDR | N | FAIL
| Project Manager | [11 empty] | PE - Power Electronics | PE | CDR
| Lead Engineer | [11 empty] | DE - Digitial Electronics | DE | TRR
| Description of Project | [11 empty] | ME - Mechanical Engineer | ME
| Customer | [11 empty] | PM - Program Manager | PM
| Key deliverable schedule | [11 empty] | ECAD - ECAD Engineer | ECAD
| Security Classififcation | [11 empty] | ESE - Embedded Software Engineer | ESE
Date of Gate Review
| Category | Item | Description | PASS/FAIL | Evidence (Screen Shots/ Jama Links/ File Location) | Notes / Actions | Action Status | Action Due Date | Who | Reviewer (Titles) | Reviewed (Y/N) | Phase Gate Needed
| Schematic | Netlist Integrity | Does the PCB netlist exactly match the schematic without missing or extra connections? | [8 empty] | CDR
| Schematic | Component Values | Are all component values consistent with the schematic and design intent? | [8 empty] | PDR
| Schematic | Footprint Mapping | Are all footprints correctly assigned and verified against datasheets? | [8 empty] | CDR
| Schematic | Pin Connectivity | Are all pins correctly connected with no unintended floating nodes? | [8 empty] | PDR
| Schematic | Power Nets | Are all power and ground nets correctly assigned and not unintentionally shorted or split?
| Schematic | Critical Nets | Are all critical nets (clock, RF, high-speed, analog) correctly identified and preserved?
| Schematic | Pin Swaps | Are all pin/gate swaps verified and documented?
| Schematic | Decoupling Presence | Are all required decoupling capacitors present per IC requirements?
| Stack-up | Layer Count | Is the selected layer count appropriate for signal integrity, power, and EMI needs?
| Stack-up | Symmetry | Is the stack-up symmetrical to prevent board warpage during fabrication?
| Stack-up | Dielectric Thickness | Are dielectric thicknesses defined and consistent with impedance targets?
| Stack-up | Copper Weight | Are copper weights defined appropriately for each layer’s function?
| Stack-up | Material Selection | Are materials (e.g., FR-4, Rogers) suitable for frequency, loss, and thermal requirements?
| Stack-up | Impedance Control | Are controlled impedance layers clearly defined and documented?
| Stack-up | Reference Planes | Does every signal layer have an adjacent solid reference plane?
| Stack-up | Plane Pairing | Are power and ground planes properly paired to reduce PDN impedance?
| Power | Ground Plane Integrity | Is there a continuous, unbroken ground plane with no unnecessary splits?
| Power | Return Paths | Are low-impedance return paths maintained for all signals?
| Power | Bulk Decoupling | Are bulk capacitors sized and placed correctly for low-frequency stability?
| Power | High-Frequency Decoupling | Are high-frequency capacitors placed as close as possible to IC power pins?
| Power | Capacitor Placement | Are decoupling capacitors connected with minimal loop inductance?
| Power | IR Drop | Has IR drop been analyzed and verified within acceptable limits?
| Power | Plane Sizing | Are power planes sized adequately for expected current loads?
| Power | Ferrite Beads | Are ferrite beads used appropriately without causing instability?
| Power | Grounding Strategy | Is grounding strategy (single-point, split, or unified) appropriate for the design?
| Current | Trace Width | Are all traces sized according to expected current using validated methods?
| Current | Temperature Rise | Is temperature rise within acceptable limits under worst-case conditions?
| Current | Copper Thickness | Is copper weight properly accounted for in current calculations?
| Current | Via Current Capacity | Are vias sized and replicated sufficiently for current transitions?
| Current | Parallel Paths | Are multiple vias or traces used where necessary to share current?
| Current | Loop Area | Are high-current loops minimized to reduce EMI and losses?
| Signal Integrity | Controlled Impedance | Are impedance-controlled traces designed and verified?
| Signal Integrity | Differential Pairs | Are differential pairs routed with consistent spacing and symmetry?
| Signal Integrity | Length Matching | Are critical signals length-matched within tolerance requirements?
| Signal Integrity | Stub Minimization | Are stubs eliminated or minimized on high-speed signals?
| Signal Integrity | Termination | Are proper termination schemes implemented where required?
| Signal Integrity | Via Usage | Are vias minimized on high-speed paths or properly back-drilled?
| Signal Integrity | Return Path Continuity | Are return paths continuous across layer transitions?
| Signal Integrity | Crosstalk | Is spacing sufficient to minimize crosstalk between signals?
| Signal Integrity | Reference Planes | Do all high-speed traces reference continuous planes?
| EMI | Loop Area | Are high dI/dt loop areas minimized?
| EMI | Ground Shielding | Is a solid ground plane used to shield noisy circuits?
| EMI | Filtering | Are filters properly placed at I/O boundaries?
| EMI | Stitching Vias | Are stitching vias used to contain EMI and maintain return paths?
| EMI | Domain Separation | Are analog, digital, and RF sections properly isolated?
| EMI | Edge Rates | Are edge rates controlled where necessary to reduce emissions?
| Placement | Functional Grouping | Are components grouped logically by function?
| Placement | Signal Flow | Does placement follow natural signal flow (input → output)?
| Placement | Critical Components | Are critical components placed first and optimally?
| Placement | Decoupling Location | Are decoupling capacitors placed adjacent to IC pins?
| Placement | Noise Isolation | Are sensitive components isolated from noisy regions?
| Placement | Orientation | Are components oriented consistently for assembly and readability?
| Placement | Mechanical Safety | Are components clear of mounting holes and stress areas?
| Mechanical | Board Outline | Does the PCB outline match the enclosure design?
| Mechanical | Mounting Holes | Are hole sizes, plating, and tolerances correctly defined?
| Mechanical | Copper Clearance | Is copper cleared adequately around mounting holes?
| Mechanical | Keep-Out Zones | Are all mechanical keep-out areas respected?
| Mechanical | Connector Alignment | Are connectors aligned with enclosure openings?
| Mechanical | Height Constraints | Are all component height limits satisfied?
| Mechanical | Edge Clearance | Is sufficient clearance maintained from board edges?
| Mechanical | Fiducials | Are global and local fiducials included?
| Thermal | Heat Sources | Are all heat-generating components identified?
| Thermal | Thermal Vias | Are thermal vias used effectively under power devices?
| Thermal | Heat Spreading | Are copper pours used for thermal dissipation?
| Thermal | Airflow | Is airflow direction considered in placement?
| Thermal | Thermal Isolation | Are sensitive components isolated from heat sources?
| Routing | Routing Cleanliness | Is routing clean without unnecessary jogs or complexity?
| Routing | Trace Consistency | Are trace widths consistent for similar nets?
| Routing | Corners | Are sharp angles avoided (no acute angles)?
| Routing | Via Count | Is via usage minimized in critical paths?
| Routing | Clearance | Are spacing rules met across all nets?
| Routing | Dangling Copper | Is all unused copper removed or properly grounded?
| DFM | Trace/Space Limits | Does the design meet fab minimum trace/space rules?
| DFM | Annular Ring | Are annular ring requirements satisfied?
| DFM | Drill Sizes | Are drill sizes standardized and within limits?
| DFM | Solder Mask | Is solder mask properly defined without slivers?
| DFM | Silkscreen | Is silkscreen readable and not overlapping pads?
| DFM | Panelization | Has panelization been considered or defined?
| DFA | Component Orientation | Are components oriented consistently for assembly?
| DFA | Polarity Marking | Are polarity indicators clear and visible?
| DFT | Test Points | Are test points provided for all critical signals?
| DFT | Accessibility | Are test points accessible for probes/fixtures?
| DFT | Debug Interfaces | Are programming/debug ports accessible?
| Reliability | ESD Protection | Is ESD protection implemented at all external interfaces?
| Reliability | Surge Protection | Are surge/transient protections included where needed?
| Reliability | Derating | Are components properly derated for reliability?
| Reliability | Creepage/Clearance | Are safety distances compliant with voltage requirements?
| Reliability | Environment | Are environmental factors (temp, vibration, humidity) considered?
| Documentation | Fab Files | Are Gerber/ODB++ files validated and correct?
| Documentation | Drill Files | Are drill files accurate and aligned with layout?
| Documentation | Stack-up | Is the stack-up clearly documented for fabrication?
| Documentation | Impedance Specs | Are impedance requirements specified to the manufacturer?
| Documentation | BOM | Does the BOM match the final approved design?
Notes: (record any key points discussed but not covered elsewhere)
| Gate Outcome: |  |  | Date of next review
Approval:
| Technical Lead |  |  | Date:
| System Engineer |  |  | Date:
| SME Electrical Engineer |  |  | Date:
| ECAD Engineer |  |  | Date:
| Mechanical Engineer |  |  | Date:
| Program Manager |  |  | Date:
| Design Engineering Manager |  |  | Date:
| Director of Engineering |  |  | Date:

## Mechanical Review (Phase 3)
Confidentiality Notice: This document is private and confidential. If received in error, please destroy and notify TT Electronics (TT). TT does not intend to waive confidentiality or privilege. Dissemination, use of or reliance upon this document is prohibited when received in error. © TT Electronics PLC
Mechanical Review Checklist (PDR/CDR)
[13 empty] | SE - System Engineer | SE | SRR | Y | PASS
| Title of Project | [11 empty] | LE - Lead Engineer | LE | PDR | N | FAIL
| Project Manager | [11 empty] | PE - Power Electronics | PE | CDR
| Lead Engineer | [11 empty] | DE - Digitial Electronics | DE | TRR
| Description of Project | [11 empty] | ME - Mechanical Engineer | ME
| Customer | [11 empty] | PM - Program Manager | PM
| Key deliverable schedule | [11 empty] | ECAD - ECAD Engineer | ECAD
| Security Classififcation | [11 empty] | ESE - Embedded Software Engineer | ESE
Date of Gate Review
| Category | Item | Description | PASS/FAIL | Evidence (Screen Shots/ Links/ File Location) | Notes / Actions | Action Status | Action Due Date | Who | Reviewer (Titles) | Reviewed (Y/N) | Phase Gate Needed
| Requirements | Traceability | Does the enclosure design trace to all system and subsystem requirements? | [8 empty] | CDR
| Requirements | Functional Compliance | Does the enclosure fully support all functional requirements (protection, mounting, interfaces)? | [8 empty] | PDR
| Requirements | Environmental | Does the design meet all environmental requirements (temperature, vibration, shock, humidity)? | [8 empty] | CDR
| Requirements | Sealing | Are ingress protection (IP rating) or sealing requirements met? | [8 empty] | PDR
| Requirements | Structural | Does the enclosure meet structural load requirements?
| Requirements | Safety | Are all safety requirements and hazard mitigations implemented?
| Requirements | Margins | Are mechanical and thermal margins defined and acceptable?
| Integration | PCB Fit | Do all PCBs fit within the enclosure with proper clearances?
| Integration | Component Clearance | Are internal component height and keep-outs respected?
| Integration | Cable Routing | Is cable routing defined, protected, and strain-relieved?
| Integration | Connector Access | Are all connectors accessible and properly aligned?
| Integration | Assembly Sequence | Is the assembly sequence logical and feasible?
| Integration | Serviceability | Can the unit be serviced or disassembled if required?
| Integration | Tolerance Stack-Up | Has tolerance stack-up been analyzed and validated?
| Structure | Load Cases | Have all load cases (static, dynamic, shock) been defined?
| Structure | Stress Analysis | Has FEA or hand analysis verified stresses are within limits?
| Structure | Factor of Safety | Are factors of safety appropriate for aerospace/defense standards?
| Structure | Fastener Design | Are fasteners correctly sized, spaced, and secured?
| Structure | Thread Engagement | Is sufficient thread engagement provided for all fasteners?
| Structure | Vibration Analysis | Does the design prevent loosening under vibration?
| Structure | Resonance | Have natural frequencies been analyzed to avoid resonance?
| Thermal | Heat Sources | Are all internal heat sources identified and quantified?
| Thermal | Thermal Path | Are conductive/convective thermal paths clearly defined?
| Thermal | Cooling Strategy | Is cooling strategy (passive/active) sufficient for worst-case conditions?
| Thermal | Interface Materials | Are thermal interface materials specified and appropriate?
| Thermal | Thermal Limits | Are all components maintained within temperature limits?
| Thermal | Analysis | Has thermal simulation or testing validated performance?
| EMI | Shielding Effectiveness | Does the enclosure provide required EMI shielding effectiveness?
| EMI | Gasketing | Are conductive gaskets used where necessary?
| EMI | Seams & Joints | Are seams designed to minimize EMI leakage?
| EMI | Grounding | Is chassis grounding strategy clearly defined?
| EMI | Cable Shield Termination | Are cable shields properly terminated to the enclosure?
| EMI | Apertures | Are openings minimized and controlled for EMI performance?
| Materials | Material Selection | Are materials appropriate for strength, weight, and environment?
| Materials | Corrosion Resistance | Are materials and coatings resistant to corrosion?
| Materials | Compatibility | Are dissimilar metals managed to prevent galvanic corrosion?
| Materials | Outgassing | Are materials compliant with outgassing requirements (if applicable)?
| Materials | Coatings | Are coatings/anodizing/paint specified and appropriate?
| Materials | Flammability | Do materials meet flammability requirements?
| Hardware | Fastener Selection | Are fasteners appropriate for load and environment?
| Hardware | Locking Features | Are locking mechanisms (Loctite, lock washers, safety wire) defined?
| Hardware | Standardization | Are standard fasteners used where possible?
| Hardware | Accessibility | Are all fasteners accessible for assembly?
| Hardware | Torque Specs | Are torque requirements defined?
| DFM | Process Selection | Are manufacturing processes (machining, casting, sheet metal) appropriate?
| DFM | Tolerances | Are tolerances realistic and manufacturable?
| DFM | Complexity | Is the design free from unnecessary manufacturing complexity?
| DFM | Tool Access | Is tool access sufficient for machining/assembly?
| DFM | Cost | Is the design optimized for cost at target volumes?
| DFM | Yield | Are risks to manufacturing yield minimized?
| DFA | Assembly Sequence | Is the assembly sequence efficient and error-resistant?
| DFA | Alignment Features | Are alignment features (pins, bosses) included?
| DFA | Human Factors | Is assembly feasible with standard tools and ergonomics?
| DFA | Error Proofing | Are features included to prevent incorrect assembly?
| DFA | Part Count | Is part count minimized?
| Sealing | Gasket Design | Are gaskets properly specified and compressed?
| Sealing | IP Rating | Does the design meet required IP rating?
| Sealing | Moisture Control | Are moisture ingress and condensation addressed?
| Sealing | Pressure Equalization | Are vents or pressure equalization features included if needed?
| Sealing | Dust Protection | Is dust ingress prevented?
| Test | Test Plan | Is there a defined mechanical verification test plan?
| Test | Vibration Testing | Is vibration testing planned and representative?
| Test | Thermal Testing | Is thermal testing defined for worst-case conditions?
| Test | Environmental Testing | Are environmental tests (humidity, salt fog, etc.) defined?
| Test | Inspection | Are inspection criteria defined (CMM, visual, etc.)?
| Documentation | Drawings | Are all mechanical drawings complete and released?
| Documentation | GD&T | Is GD&T correctly applied and sufficient?
| Documentation | BOM | Is mechanical BOM complete and accurate?
| Documentation | Revision Control | Is the design under proper configuration control?
| Documentation | Notes | Are critical manufacturing and assembly notes included?
| Gotchas | Tolerance Stack-Up | Has tolerance stack-up been underestimated or skipped?
| Gotchas | Thermal Expansion | Are thermal expansion mismatches accounted for?
| Gotchas | Fastener Loosening | Is there risk of fasteners loosening under vibration?
| Gotchas | EMI Leakage | Are seams and gaps unintentionally radiating?
| Gotchas | Assembly Issues | Are there hidden assembly access problems?
Notes: (record any key points discussed but not covered elsewhere)
| Gate Outcome: |  |  | Date of next review
Approval:
| Technical Lead |  |  | Date:
| System Engineer |  |  | Date:
| Embedded Electronics (Digital) Engineer |  |  | Date:
| Power Electronics Engineer |  |  | Date:
| Mechanical Engineer |  |  | Date:
| Program Manager |  |  | Date:
| Design Engineering Manager |  |  | Date:
| Director of Engineering |  |  | Date:

## Test Readiness (Phase 4)
Confidentiality Notice: This document is private and confidential. If received in error, please destroy and notify TT Electronics (TT). TT does not intend to waive confidentiality or privilege. Dissemination, use of or reliance upon this document is prohibited when received in error. © TT Electronics PLC
Test Readiness Review Checklist (TRR)
[12 empty] | SE - System Engineer | SE | SRR | Y | PASS
| Title of Project | [10 empty] | LE - Lead Engineer | LE | PDR | N | FAIL
| Project Manager | [10 empty] | PE - Power Electronics | PE | CDR
| Lead Engineer | [10 empty] | DE - Digitial Electronics | DE | TRR
| Description of Project | [10 empty] | ME - Mechanical Engineer | ME
| Customer | [10 empty] | PM - Program Manager | PM
| Key deliverable schedule | [10 empty] | ECAD - ECAD Engineer | ECAD
| Security Classififcation | [10 empty] | ESE - Embedded Software Engineer | ESE
Date of Gate Review
| Category | Item | Description | PASS/FAIL | Evidence (Screen Shots/ Links/ File Location) | Notes / Actions | Action Status | Action Due Date | Who | Reviewer (Titles) | Reviewed (Y/N)
| Test Planning | Test Plan Completeness | Is there a complete, approved test plan covering all requirements?
| Test Planning | Requirement Traceability | Does every requirement map to at least one verification test?
| Test Planning | Test Procedures | Are detailed test procedures defined and reviewed?
| Test Planning | Acceptance Criteria | Are clear pass/fail criteria defined for each test?
| Test Planning | Test Environment | Are environmental conditions defined for each test?
| Test Planning | Equipment Readiness | Is all required test equipment available and calibrated?
| Test Planning | Safety Procedures | Are safety procedures defined for all test activities?
| Test Planning | Configuration Control | Is the test article configuration documented and controlled?
| Bring-Up | Visual Inspection | Has the hardware passed visual and workmanship inspection?
| Bring-Up | Power-On Safety | Does the system power up without damage or abnormal current draw?
| Bring-Up | Power Rails | Are all power rails within tolerance at startup and steady state?
| Bring-Up | Inrush Current | Is inrush current within expected limits?
| Bring-Up | Thermal Check | Are any components overheating during initial operation?
| Bring-Up | Basic Functionality | Does the system perform basic expected functions?
| Bring-Up | Firmware Load | Can firmware/software be reliably loaded and executed?
| Bring-Up | Debug Access | Are debug interfaces functional and accessible?
| Electrical | Voltage Accuracy | Are all voltage rails within specified tolerance across conditions?
| Electrical | Current Consumption | Does current consumption match expected values in all modes?
| Electrical | Efficiency | Does power conversion efficiency meet design targets?
| Electrical | Ripple & Noise | Are voltage ripple and noise within acceptable limits?
| Electrical | Transient Response | Does the system handle load transients within specification?
| Electrical | Stability | Are power supplies stable under all operating conditions?
| Electrical | Signal Levels | Are signal voltage levels correct and compliant with interfaces?
| Functional | Requirement Coverage | Are all functional requirements verified through testing?
| Functional | Modes of Operation | Are all operating modes tested and validated?
| Functional | Edge Cases | Are edge cases and corner conditions tested?
| Functional | Fault Handling | Does the system respond correctly to fault conditions?
| Functional | Interfaces | Do all interfaces operate correctly under load?
| Functional | Timing | Are timing and latency requirements met?
| Thermal | Temp Range | Does the system operate across the full temperature range?
| Thermal | Hot Spots | Are there any thermal hotspots exceeding limits?
| Thermal | Thermal Cycling | Does the system survive thermal cycling?
| Environmental | Vibration | Does the system pass vibration testing?
| Environmental | Shock | Does the system survive mechanical shock events?
| Environmental | Humidity | Does the system perform under humidity exposure?
| Environmental | Altitude | Does the system operate correctly at altitude/pressure conditions?
| Power | Input Range | Does the system operate across full input voltage range?
| Power | Transients | Does the system handle input transients and disturbances?
| Power | Startup | Is startup behavior consistent and safe under all conditions?
| Power | Shutdown | Is shutdown behavior controlled and safe?
| Power | Protection | Do protection mechanisms trigger correctly?
| Mechanical | Fit & Finish | Does the hardware fit correctly within the enclosure?
| Mechanical | Connectors | Are connectors secure and reliable under use?
| Mechanical | Fasteners | Do fasteners remain secure under vibration and use?
| Mechanical | Cable Strain | Are cables properly strain-relieved during operation?
| Mechanical | Wear & Tear | Are there signs of wear during testing?
| Test Infra | Test Fixtures | Are test fixtures reliable and repeatable?
| Test Infra | Automation | Are tests automated where appropriate?
| Test Infra | Data Logging | Is all relevant test data captured and stored?
| Test Infra | Repeatability | Are test results consistent across runs?
| Documentation | Test Reports | Are all test results documented clearly?
| Documentation | Traceability Matrix | Is requirement-to-test traceability complete?
| Documentation | Failure Reports | Are failures documented with root cause analysis?
| Documentation | Configuration | Is tested configuration clearly documented?
| Documentation | Sign-Off | Are test results formally reviewed and approved?
Notes: (record any key points discussed but not covered elsewhere)
| Gate Outcome: |  |  | Date of next review
Approval:
| Technical Lead |  |  | Date:
| System Engineer |  |  | Date:
| Embedded Electronics (Digital) Engineer |  |  | Date:
| Power Electronics Engineer |  |  | Date:
| Test Engineer |  |  | Date:
| Mechanical Engineer |  |  | Date:
| Program Manager |  |  | Date:
| Design Engineering Manager |  |  | Date:
| Director of Engineering |  |  | Date: