## Data
Synthetic POC Data. Not TT Electronics Product Data. Not for Design, Fabrication, Certification, Procurement, or Production.
Project: EVINV-POC-001 ¦ Product: EV-INV-800 ¦ Phase: 6 ¦ Gate: 6 ¦ Generated: 2026-08-18T21:33:34.786Z
Deliverable ID | PPAP Element | Customer Criterion | Required Evidence | Status | Responsible | Priority
PPAP-001 | Design Records (Final BOM Rev D) | Released BOM per CUST-PPAP-001 §3.1 | Released BOM with ECN sign-off | Complete | Engineering Manager | High
PPAP-002 | Approved Engineering Change Documents | All ECNs signed per change control process | ECN register with approval signatures | Complete | Engineering Manager | High
PPAP-003 | Process Flow Diagram | Detailed assembly/test flow per APQP §4 | Process flow map RPT-FLOW-001 | Complete | Manufacturing Engineering | High
PPAP-004 | Process FMEA | PFMEA covering all critical characteristics | PFMEA-EVINV-001 with RPN scoring | Complete | Quality Engineering | High
PPAP-005 | Process Capability Study (Cpk ≥ 1.33) | Cpk ≥ 1.33 for all critical characteristics | Cpk study per EVINV-POC-STD-001 §5.1 | Action Required — Solder Joint Cpk below threshold | Quality Engineering | Critical
PPAP-006 | First Article Inspection Report | FAI per AS9102 or equivalent | FAI report FAI-EVINV-001 | In Progress | Quality Engineering | High
PPAP-007 | Dimensional Results (GD&T) | All critical dimensions within tolerance | CMM report DIM-EVINV-001 | Complete | Manufacturing Engineering | Medium