## Data
Synthetic POC Data. Not TT Electronics Product Data. Not for Design, Fabrication, Certification, Procurement, or Production.
Project: EVINV-POC-001 ¦ Product: EV-INV-800 ¦ Phase: 7 ¦ Gate: 7 ¦ Generated: 2026-08-18T21:38:20.987Z
Lesson ID | Category | Phase | Description | Root Cause | Corrective Action | Applicable Future | Status
LL-001 | Process Variability | Phase 6–7 | Torque variation in MOP-012 bracket mounting operation (2.1–4.8 N·m; spec 3.5±0.5 N·m). Torque wrench calibration inconsistency and operator technique variation. | Manual torque wrench without torque indication feedback; operator variability in technique | Upgrade to click-type torque wrench with calibration certificate; implement operator re-training and SPC monitoring for this operation. | Apply to all torque-sensitive assembly operations in future NPI programs | Action In Progress
LL-002 | DFM/Assembly | Phase 3 | Coolant connector orientation (A3-001) required design change. Early DFM review should include 3D assembly simulation. | Insufficient assembly access analysis at preliminary design stage | Add assembly access simulation to Phase 3 DFM checklist for future programs. | Phase 3 DFM review — all future NPI programs | Closed
LL-003 | Quality / Cpk | Phase 6 | Solder joint Cpk below threshold on first qualification build (Cpk 0.87 vs 1.33). Reflow profile required adjustment. | Reflow profile not optimized for new 800V-class power module pad geometry | Optimize reflow profile early in Phase 5; perform Cpk pilot run before Phase 6 qualification. | Phase 5 validation planning for future high-power programs | Closed
LL-004 | Requirements | Phase 2 | REQ-THERM-004 initial revision lacked measurable acceptance criterion. Added TP-CASE-1 thermocouple criterion in Phase 2. | Requirements review missed testability of thermal stability requirement | Apply RequirementTestability check at requirements stage for all future programs. | Phase 2 requirements review — all future NPI programs | Closed
LL-005 | Supply Chain | Phase 8 | Primary SiC power module IGBT-HV-800-A received PDN (discontinuance notice). EOL process initiated. | Supplier lifecycle monitoring not integrated into Phase 4/6 reviews | Integrate supplier lifecycle feed into Phase 4 BOM health check for future programs. | Phase 4 CDR BOM health check — all future NPI programs | Open (EOL process ongoing)