## Read Me
Customer Production-Readiness Package
Project ID | EVINV-POC-001
Product | EV-INV-800 Demonstration Traction Inverter
Lifecycle | Phase 6 / Gate 6
Version | 1.0
Status | Synthetic POC Input
Notice | Synthetic POC Data - Not TT Electronics Product Data - Not for Design, Fabrication, Certification, Procurement, or Production.

## Criteria
Criterion ID | PPAP / FAI Deliverable | Customer Criterion | Required Evidence | Applicability | Acceptance Threshold | Responsible Role | Timing | Priority | Expected Status
PR-001 | Process flow | Approved production flow | Controlled process flow | Applicable | Approved | Manufacturing Engineer | Before Gate 6 | High | Complete
PR-002 | PFMEA | Critical risks controlled | PFMEA extract | Applicable | No uncontrolled high risk | Quality Engineer | Before Gate 6 | High | Complete
PR-003 | Control plan | Critical characteristics controlled | Control plan | Applicable | All critical items covered | Quality Engineer | Before Gate 6 | High | Complete
PR-004 | FAI | First article accepted | FAI summary | Applicable | All characteristics accepted | Quality Engineer | Before Gate 6 | High | Complete
PR-005 | Capability | Critical dimensions capable | Capability data | Applicable | Cpk >=1.33 | Manufacturing Engineer | Before Gate 6 | High | Complete
PR-006 | Work instructions | Operator instructions released | Released WI | Applicable | Released | Operations Lead | Before Gate 6 | Medium | Complete
PR-007 | Equipment qualification | Equipment qualified | Qualification record | Applicable | Approved | Manufacturing Engineer | Before Gate 6 | High | Complete
PR-008 | Training | Operators trained | Training record | Applicable | 100 percent assigned staff | Operations Lead | Before Gate 6 | Medium | Complete