## Data
Synthetic POC Data. Not TT Electronics Product Data. Not for Design, Fabrication, Certification, Procurement, or Production.
Project: EVINV-POC-001 ¦ Product: EV-INV-800 ¦ Phase: 3 ¦ Gate: 3 ¦ Generated: 2026-08-18T13:22:49.735Z
Finding ID | Category | Description | Severity | Affected Component | Risk Level | Recommended Action
F3-001 | Assembly Access | Coolant connector (CN-COOL-1) orientation creates assembly-access concern. Connector insertion angle obstructs access to M4 fasteners J-FAST-7 through J-FAST-10. | Major | CN-COOL-1 | High — may cause assembly difficulty and rework during production build | Revise coolant connector orientation in detailed design to ensure unobstructed access to J-FAST-7 through J-FAST-10. Provide revised drawing for Phase 4 verification.
F3-002 | HV Layout (Preliminary) | HV bus routing at preliminary stage shows tight clearance zone near gate driver section. Requires verification in detailed layout. | Minor | VBUS+ | Medium — to be confirmed in Phase 4 HV clearance check | Monitor in Phase 4 detailed design review; HV clearance check will quantify.
F3-003 | DFM Rule Compliance | Preliminary BOM lists SiC power module IGBT-HV-800-A — verify PCN/PDN status before design freeze. | Observation | Q_HV_1 | Low — will be confirmed in Phase 4 supplier feed check | Request latest lifecycle status from supplier before Phase 4 CDR.