## Data
Synthetic POC Data. Not TT Electronics Product Data. Not for Design, Fabrication, Certification, Procurement, or Production.
Project: EVINV-POC-001 ¦ Product: EV-INV-800 ¦ Phase: 6 ¦ Gate: 6 ¦ Generated: 2026-08-19T02:42:14.044Z
MRL Element | Description | Evidence | Current MRL | Target MRL | Gap | Status
MRL-4 | Capability to produce technology in lab | LAB-VERIFY-001 | 4 | 7 | Process scaling required | In Progress
MRL-5 | Capability to produce prototype components in production environment | PROTO-BUILD-001 | 5 | 7 | PPAP completion required | In Progress
MRL-6 | Capability to produce prototype systems in production environment | MFG-DEMO-001 | 6 | 7 | Minor — process refinement | Near Complete
MRL-7-SQ | Statistical Quality — Cpk ≥ 1.33 for critical characteristics | CPK-RPT-001 | Partial | 7 | Solder joint Cpk below threshold — corrective action in progress | Action Required
MRL-7-DOC | Production documentation complete (BOM, routes, WI, SOP) | DOC-PKG-001 | 7 | 7 | None | Complete
MRL-7-EQ | Equipment qualification complete | EQUIP-QUAL-001 | 7 | 7 | None | Complete